## Project Data
Project ID | Project Name | Owner | Department | Start Date | End Date | Status | % Complete | Budget (₹L) | Spent (₹L) | Priority | Notes
P001 | Student Portal Upgrade | Ravi Kumar | IT | 2026-01-15 | 2026-06-30 | Completed | 100% | 12.5 | 12.1 | High | Deployed to production
P002 | JEE Mock Test Platform | Priya Singh | Academics | 2026-02-01 | 2026-08-31 | In Progress | 65% | 8 | 5.2 | High | UI review pending
P003 | NEET Study Material Refresh | Amit Verma | Content | 2026-03-10 | 2026-07-15 | In Progress | 40% | 5.5 | 2.2 | Medium | Writer assigned
P004 | RRB Data Analytics Dashboard | Sunita Rao | IT | 2026-01-05 | 2026-05-31 | At Risk | 55% | 6 | 4.8 | High | Delay in API integration
P005 | SSC CGL Batch Planning | Deepak Joshi | Operations | 2026-04-01 | 2026-09-30 | Not Started | 0% | 3 | 0 | Low | Awaiting approvals
P006 | CUET Coaching Expansion | Neha Gupta | Academics | 2026-02-20 | 2026-10-31 | In Progress | 30% | 15 | 4.5 | High | 3 new centres onboarded
P007 | ERP Integration | Vikram Nair | IT | 2025-11-01 | 2026-04-30 | On Hold | 70% | 20 | 14 | Medium | Vendor issue
P008 | SATHEE Baseline Assessment | Anjali Mehta | Academics | 2026-03-01 | 2026-06-15 | Completed | 100% | 4 | 3.9 | High | All 1200 students assessed
P009 | Faculty Training Programme | Rahul Das | HR | 2026-05-01 | 2026-07-31 | In Progress | 20% | 2.5 | 0.5 | Medium | Module 1 done
P010 | Mobile App Development | Kavita Sharma | IT | 2026-04-15 | 2026-12-31 | Not Started | 0% | 18 | 0 | High | RFP issued

## Summary
Status | Count | Department | Budget (₹L) | Spent (₹L)
Completed | 2 | IT | 56.5 | 30.9
In Progress | 4 | Academics | 27 | 13.6
On Hold | 1 | Content | 5.5 | 2.2
At Risk | 1 | Operations | 3 | 0
Not Started | 2 | HR | 2.5 | 0.5

## Dashboard
📊 PROJECT STATUS DASHBOARD
Generated: 25 June 2026 ¦ Total Projects: 10
Total Projects |  | Completed |  | In Progress |  | At Risk |  | On Hold | Not Started
10 |  | 2 |  | 4 |  | 1 |  | 1 | 2
ID | Project Name | Owner | Status | Priority | %Done | Budget | Spent | Variance
P001 | Student Portal Upgrade | Ravi Kumar | Completed | High | 100% | 12.5 | 12.1 | 0.4
P002 | JEE Mock Test Platform | Priya Singh | In Progress | High | 65% | 8 | 5.2 | 2.8
P003 | NEET Study Material Refresh | Amit Verma | In Progress | Medium | 40% | 5.5 | 2.2 | 3.3
P004 | RRB Data Analytics Dashboard | Sunita Rao | At Risk | High | 55% | 6 | 4.8 | 1.2
P005 | SSC CGL Batch Planning | Deepak Joshi | Not Started | Low | 0% | 3 | 0 | 3
P006 | CUET Coaching Expansion | Neha Gupta | In Progress | High | 30% | 15 | 4.5 | 10.5
P007 | ERP Integration | Vikram Nair | On Hold | Medium | 70% | 20 | 14 | 6
P008 | SATHEE Baseline Assessment | Anjali Mehta | Completed | High | 100% | 4 | 3.9 | 0.1
P009 | Faculty Training Programme | Rahul Das | In Progress | Medium | 20% | 2.5 | 0.5 | 2
P010 | Mobile App Development | Kavita Sharma | Not Started | High | 0% | 18 | 0 | 18